## High_Level_Sprints
Sprint | Timeframe (approx) | Goal
0 | Feb3–Feb 9 | Scope NEMSIS subset (~200 GB source), ingest selected parts, do EDA, cleaning, consolidation
1 | Feb 10–16 | Use Databricks on scoped subset; run simple→advanced models, choose best model for forecasting
2 | Feb 17–23 | Implement forecasting with chosen model and build initial dashboard/reporting
3 | Feb 24–27 | Polish entire subset workflow (data→model→dashboard) for midterm check-in
4 | Feb 28–Mar 6 | Return to larger data; renewed scoping, cleaning, and consolidation at bigger scale
5 | Mar 7–13 | Apply models on larger dataset, evaluate performance and scalability
6 | Mar 14–20 | Final best-model selection and full forecasting runs on larger data
7 | Mar 21–27 | Full-featured dashboarding and automated reporting based on final models
8 | Mar 28–Apr 5 | Overall review, evaluation, and integration of results and QA recommendations
9 | Apr 6–10 | Buffer time, final report and presentation preparation for Apr 10

## Detailed_Sprints
Sprint | Timeframe | Goal | Key tasks / deliverables
0 | Now–Feb 9 | Scope NEMSIS subset, ingest, initial EDA, cleaning, consolidation | - Review NEMSIS 200 GB structure; decide on sampling strategy (years, regions, incident types)
- Extract representative subset (e.g., 1–5 GB or 200k–500k rows)
- Load into local/Jupyter environment; profile data (row counts, missingness, distributions)
- Perform initial EDA: time-series of call volumes, injury flag frequencies, shift patterns
- Light cleaning: handle obvious nulls, standardize date/time formats, filter invalid records
- Consolidate into single cleaned CSV/Parquet for Sprint 1 modeling
- Document scoping decisions and EDA findings in notebook
1 | Feb 10–16 | Use Databricks on subset; run simple→advanced models, choose best for forecasting | - Set up Databricks Community Edition cluster; upload cleaned subset
- Engineer features: hour-of-day, day-of-week, call type, crew size, shift indicators
- Train baseline model: linear regression for daily/hourly call volume forecast
- Train advanced models: logistic regression (peak/no-peak), random forest, gradient boosting
- Evaluate models: compare accuracy, MAE/RMSE, recall on peak periods
- Select best model based on performance and interpretability for EMS use case
- Log results in MLflow or notebook; document model choice rationale
2 | Feb 17–23 | Implement forecasting with chosen model + initial dashboard/reporting | - Use best model from Sprint 1 to generate demand forecasts for next week/month
- Identify high-risk periods (e.g., volume > 75th percentile) linked to injury risk
- Build initial Streamlit dashboard: call volume over time, forecast vs actual, peak windows
- Add 2–3 charts: calls by hour, injury-related incidents by shift, regional breakdown if feasible
- Create simple automated report: text output summarizing forecast and high-risk windows
- Test dashboard end-to-end on Databricks outputs; ensure reproducibility
3 | Feb 24–27 | Polish subset pipeline, models, and dashboard for midterm check-in (Feb 27) | - Refine dashboard labels, titles, and layout for clarity
- Add narrative text connecting visuals to EMS injury problem and QA goals
- Prepare 3–5 slide deck or talking points for midterm: problem, data, model, early insights
- Run end-to-end pipeline to confirm it works smoothly (ingest → clean → model → dashboard)
- Capture screenshots or screen recording of dashboard for submission
- Document any limitations or next steps for post-midterm work
- Deliver midterm check-in demo on Feb 27
4 | Feb 28–Mar 6 | Scale to larger NEMSIS slice; renewed scoping, cleaning, consolidation | - Review full 200 GB NEMSIS dataset; decide on expanded sample size (e.g., 10–20 GB or millions of rows)
- Extract larger representative subset balancing years, regions, injury types, incident diversity
- Re-run data profiling: assess new missingness patterns, outliers, data quality at scale
- Expand cleaning pipeline: robust outlier detection (IQR), advanced imputation (KNN/median)
- Derive additional features: fatigue proxies (consecutive busy hours), location clusters, weather if available
- Consolidate larger dataset into Delta Lake or partitioned Parquet on Databricks
- Validate that expanded dataset maintains integrity and is ready for modeling
5 | Mar 7–13 | Apply models at scale; evaluate performance on larger data | - Re-train baseline and advanced models on expanded dataset in Databricks
- Assess how models scale: training time, memory, convergence behavior
- Evaluate performance: accuracy, precision, recall on peak detection and injury-linked patterns
- Compare results to Sprint 1 subset models; check if patterns hold or new insights emerge
- Tune hyperparameters if needed (grid search or random search on critical models)
- Log all runs and metrics in MLflow; track model versions
- Document findings: does larger data improve forecast accuracy? Any new injury correlations?
6 | Mar 14–20 | Final best-model selection + full forecasting runs | - Compare all candidate models across baseline and advanced methods
- Select final best model(s) for: (1) demand forecasting, (2) injury risk prediction if separate
- Justify selection based on accuracy (target 75%+), interpretability, and operational feasibility
- Run full forecasting: generate predictions for upcoming weeks/months across regions or shifts
- Validate forecasts against hold-out test set or recent actual data
- Identify specific high-risk windows and injury hotspots (time, location, call type)
- Prepare model card or summary: features, performance, use case, limitations
7 | Mar 21–27 | Full-featured dashboarding and automated reporting | - Expand Streamlit dashboard: add model performance summary, injury hotspot maps, QA recommendation panels
- Build automated QA reporting engine: rule-based system that reads model outputs and generates recommendations
Example: "Recommend two-person lifts 18:00–22:00 in Region X on weekdays based on peak injury risk"
- Add interactivity: filters for date range, region, shift, incident type
- Integrate forecast visualizations: predicted vs actual call volumes, confidence intervals if feasible
- Test dashboard with stakeholder perspective: can EMS dispatcher or manager understand and act on it?
- Export sample reports (PDF or text) for documentation
8 | Mar 28–Apr 5 | Overall review, validation, and integration of results | - Review entire pipeline end-to-end: data scoping → cleaning → modeling → forecasting → dashboard
- Validate reproducibility: can pipeline be re-run on new NEMSIS data without breaking?
- Cross-check results against original hypotheses: did you achieve 75%+ accuracy? Identify 10–15% injury reduction opportunities?
- Integrate findings into coherent narrative: tie back to literature gaps, RIPEN goals, EMS safety impact
- Assess limitations: sampling bias, NEMSIS public-use constraints, generalizability to Canadian EMS
- Prepare draft final report sections: methods, results, discussion, recommendations
- Solicit quick feedback from advisor or partner (Solaris/EMS contact) if possible
9 | Apr 6–10 | Buffer time, final presentation prep for Apr 10 | - Finalize presentation slides: problem framing, methods, key results, dashboard demo, QA recommendations
- Prepare live demo or screen recording of dashboard and forecasting workflow
- Rehearse presentation: aim for 10–15 min with clear EMS safety narrative and data science rigor
- Address any last-minute bugs or data refresh needs
- Complete final report: abstract, intro, methods, results, discussion, references, appendices
- Package deliverables: code repo (GitHub), documented notebooks, dashboard link, final report PDF
- Deliver final presentation on Apr 10

## Gantt
AGILE
Activities | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Setup and EDA | bar: Week 1 to Week 2; Week 5
Databricks Trial | bar: Week 1 to Week 3
AI Integration Plan | bar: Week 1 to Week 2
Data Cleaning | bar: Week 2 to Week 3; Week 5
Feature Engineering | bar: Week 3; Week 6
Model Development (Simple) | bar: Week 3; Week 6
Model Development (Advanced) | bar: Week 3; Week 6
Model Selection | bar: Week 4; Week 7
AI-Driven Reporting | bar: Week 7 to Week 8
Dashboard Development & AI | bar: Week 4; Week 7 to Week 9
Final Polish / Buffer | bar: Week 4; Week 8 to Week 9
OLD
Activities | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Setup and EDA | bar: Week 1 to Week 2
Databricks Trial | bar: Week 1 to Week 3
AI Integration Plan | bar: Week 1 to Week 2
Data Cleaning | bar: Week 2 to Week 4
Feature Engineering | bar: Week 4 to Week 6
Model Development (Simple) | bar: Week 4 to Week 6
Model Development (Advanced) | bar: Week 4 to Week 6
Model Selection | bar: Week 6 to Week 7
AI-Driven Reporting | bar: Week 6 to Week 8
Dashboard Development & AI | bar: Week 7 to Week 9
Final Polish / Buffer | bar: Week 7 to Week 9

## Worklog
Date | Number of Hours | Description of Work Done
2026-01-18 | 0.5 | Meeting with Priya, initial discussion of topics
2026-01-21 | 2 | NEMSIS Data initial proposal
2026-01-23 | 0.5 | Meeting with Solaris, Tony Tsui
2026-01-24 | 1 | Initial works on the final proposal
2026-01-25 | 2 | Continue works on the final proposal
2026-01-26 | 4 | Final works on the final proposal
2026-01-30 | 2 | Review of NEMSIS website, submission of data request for the project, communication of updates to Tony
Take Datacamp course on Introduction to Databricks, Setup a community edition Databricks account,
2026-01-31 | 2 | Review data sent by NEMSIS, extract data (about 2 hrs. processing to extract 200GB data)
2026-02-03 | 2 | Update project plan to Agile format
2026-02-04 | 2 | Extracted data review

## Hypothesis
Main Question
“How can we reduce work‑related injuries for EMS staff?”
ID | Aspects | Hypothesis (plain language) | Target variable(s) | Needed fields | Why this matters (importance) | Potential Source Tables
H1 | Workload | The busier an hour is (more 911 calls), the more likely staff injuries will occur. | Injury count or injury rate per hour; injury occurred this hour (y/n) | Hourly call volume; staff injury records with date–time | If true, predicting busy hours lets you anticipate high‑risk periods and strengthen staffing and safety then. | Calls table: PUBPCREvents (or similar) with PcrKey, CallStartTime → aggregated to hourly call volume. Injury table: StaffInjuries with InjuryID, InjuryDateTime.
H2 | Staffing | When workload is high but staffing is too low, injury risk is higher than in well‑staffed busy hours. | Injury rate per hour or shift; injury during high‑strain/under‑staffed periods (y/n) | Hourly call volume; staffing per hour/shift; injury records with time & crew | If true, you can tune staffing levels so busy periods don’t become dangerous overload for small crews. | Calls: PUBPCREvents with timestamps → hourly volume. Staffing: StaffSchedule with StaffID, UnitID, ShiftStart, ShiftEnd. Injuries: StaffInjuries with StaffID, InjuryDateTime.
H3 | Shift-Length | The longer a staff member’s shift, the more likely an injury will occur in that shift. | Injury on this shift (y/n); injury rate per 100 shifts by length | Shift schedule (start/end, length); injury records linked to shifts | If true, you can redesign shift lengths or limit very long shifts to reduce injury risk. | Schedule: StaffSchedule (StaffID, ShiftID, ShiftStart, ShiftEnd). Injuries: StaffInjuries (StaffID, InjuryDateTime, InjuryType) linked to ShiftID via time overlap.
H4 | Fatigue | Many long or consecutive shifts with little rest increase fatigue and injuries. | Injury in this week/sequence (y/n); injury rate by fatigue exposure | Shift history per person; rest time; injury records by person & date | If true, you can set rules for recovery time and maximum consecutive shifts to prevent fatigue‑related harm. | Schedule: StaffSchedule (full shift history per StaffID). Injuries: StaffInjuries with StaffID, InjuryDateTime. Derived fields: days worked in a row, rest hours.
H5 | Ergonomics | Shifts with more heavy lifting/awkward transfers have more back and shoulder injuries. | Count or rate of MSK injuries per shift or task‑load band | Call/task types; patient handling indicators; MSK injury records | If true, you can target extra support and equipment (lift aids, extra crew) when high‑lift tasks are expected. | Clinical/call detail: PUBPCREvents + PatientCareDetails with fields like PrimaryImpression, LiftingRequiredFlag, StairCarryFlag, BariatricFlag. Injuries: StaffInjuries with InjuryBodyPart.
H6 | Equioment | Lack of ergonomic equipment or its use leads to more musculoskeletal injuries. | MSK injury rate by unit/station/equipment setup | Equipment inventory by unit; which units have aids; MSK injury records | If true, it justifies investment in ergonomic gear and training at specific high‑risk units. | Assets/equipment: UnitEquipment with UnitID, HasPowerStretcher, HasLiftAssist. Deployment: UnitRoster linking StaffID to UnitID. Injuries: StaffInjuries with UnitID or shift mapping.
H7 | Culture | Crews with weaker safety culture have more work‑related injuries. | Injury rate by crew/station; safety culture score | Safety culture survey data; injury records by crew/station | If true, you can focus culture and training efforts on teams with low safety scores to reduce injuries. | Survey: SafetyCultureSurvey with CrewID / StationID, SurveyDate, SafetyScore. Injuries: StaffInjuries with CrewID / StationID (or mapped via StaffID and Shift).

## Files
ile name (folder: “ASCII_64 2024”) | Approx. size on your screen | Short description (from NEMSIS RDS 3.5 data dictionary) | Focus for phase 1?
FACTPCRDISPATCHDELAY | ~1.4 GB | Relational table with one record per EMS event per dispatch delay; stores eResponse_08 “Type of Dispatch Delay” (reasons why dispatch was delayed, e.g., call volume, weather). ​ | Yes – sample_DISPATCHDELAY
FACTPCRTURNAROUNDDELAY | ~1.4 GB | Relational table with one record per EMS event per turnaround delay; stores eResponse_12 “Type of Turn‑Around Delay” (delays in getting unit back in service at destination). ​ | Yes – sample_TURNAROUNDDELAY
Pub_PCRevents | ~38 GB (screenshot shows 37.9 GB) | Main “event” table with one row per EMS patient care report; includes all single‑entry NEMSIS elements approved for release (demographics, incident, outcome, etc.). This is the hub keyed by PcrKey that links to every FACTPCR* table. ​ | Yes – sample_Pub_PCRevents
FACTPCRRESPONSEDELAY | ~1.4 GB | Holds eResponse_09 “Type of Response Delay” (delays between dispatch and unit en route/on scene, such as traffic or crew). ​ | No (for now)
FACTPCRSCENEDELAY | ~1.4 GB | Holds eResponse_10 “Type of Scene Delay” (delays that occurred while on scene before transport). ​ | No
FACTPCRTRANSPORTDELAY | ~1.4 GB | Holds eResponse_11 “Type of Transport Delay” (delays during transport to destination). ​ | No
FACTPCRTIME | ~122 MB (labelled FACTPCRTIME in screenshot) | Time‑stamped milestones for each call: PSAP call time, unit notified, en route, on scene, at patient, left scene, at destination, transfer of care, back in service (eTimes_01, 03, 05, 06, 07, 09, 11, 12, 13). ​ | Not in current 3, but very relevant to delays later
COMPUTEDELEMENTS | ~9 GB | Derived metrics such as EMSDispatchCenterTimeSec, EMSSceneResponseTimeMin, EMSSystemResponseTimeMin, EMSTotalCallTimeMin, EMSTransportTimeMin, computed from FACTPCRTIME times. ​ | No (nice for later KPIs)
FACTPCRDESTINATIONREASON | ~1.5 GB | Contains eDisposition_20 “Reason for Choosing Destination” (e.g., closest facility, specialty center). ​ | No
FACTPCRDESTINATIONTEAM | ~2.7 GB | eDisposition_24 and eDisposition_25, destination team pre‑arrival alert/activation and its date/time. ​ | No
FACTPCRARRESTRESUSCITATION | ~1.4 GB | Elements on resuscitation efforts during cardiac arrest (subset of eArrest section). ​ | No
FACTPCRARRESTRHYTHMDESTINATION | ~1.4 GB | Cardiac rhythm on arrival at destination (eArrest_17). ​ | No
FACTPCRARRESTROSC | ~1.4 GB | Return of spontaneous circulation details for cardiac arrest events. ​ | No
FACTPCRCAUSEOFINJURY | ~1.4 GB | eInjury elements describing mechanism/cause of injury (e.g., fall, MVC). ​ | No
FACTPCRINJURYRISKFACTOR | ~1.4 GB | eInjury_03 Trauma Center Criteria and related risk factors. ​ | No
FACTPCRHOSPITALCAPABILITY | ~1.5 GB | Hospital capability data for receiving facilities (e.g., trauma, stroke, PCI). ​ | No
FACTPCRPRIMARYIMPRESSION | ~1.4 GB | eSituation primary provider impression (working diagnosis). ​ | No
FACTPCRSECONDARYIMPRESSION | ~1.4 GB | eSituation_12 provider’s secondary impressions. ​ | No
FACTPCRPROCEDURE | ~14 GB | Procedures performed (airway, IV, etc.), including times and success. ​ | No
FACTPCRPROTOCOL | ~2.2 GB | Protocols used, including eProtocol_02 (protocol age category). ​ | No
FACTPCRMEDICATION | ~16.3 GB | Medication administrations with dose, route, times. ​ | No
PCRMEDCOMPGROUP | ~2.5 GB | Links meds to complication entries (foreign key group table). ​ | No
FACTPCRVITAL | ~43.6 GB | All vital sign sets (heart rate, BP, RR, etc.) with PcrVitalKey. ​ | No
PCRVITALINTERPRETATIONGROUP | ~6.9 GB | Group table for interpretations of vitals (e.g., abnormal/normal flags). ​ | No
PCPRPROCCOMPGROUP | ~3.8 GB | Groups procedure‑related complications to procedures. ​ | No
FACTPCRBARRIERSCARE | ~1.4 GB | Barriers to patient care on scene or during transport. ​ | No
FACTPCRWORKRELATEDXPOSURE | ~229 MB | Work‑related exposure elements (e.g., provider exposure to bloodborne pathogens). ​ | No
EPROCEDURES_03REF, E SITUATION_09REF, 10REF, 11REF, 12REF | 6–29 MB | Reference tables for code sets (value lists) for procedures and situation/impression fields. ​ | No (used mostly for decoding codes)

## Pub_PCREvents
Column | Brief description (NEMSIS v3.5) | Use in phase 1?
PcrKey | Internal unique key for each EMS patient care record; used to join to all FACTPCR* tables. | Yes (primary join key)
eDispatch_01 | “Complaint Reported by Dispatch” – what dispatch said the problem was. | Probably (context for call type)
eDispatch_02 | Dispatch priority level for the response. | Maybe (triage vs delays)
eArrest_14 | Cardiac arrest outcome (e.g., ROSC, dead at scene). | No (unless study arrests)
eArrest_01, eArrest_02, eArrest_05, eArrest_07, eArrest_11, eArrest_16, eArrest_18, eArrest_20, eArrest_21, eArrest_22 | Arrest timing, witnessed status, initial rhythm, bystander CPR, ROSC, destination ROSC, etc. | No (specialized subset)
eDisposition_19 | Destination type (e.g., hospital ED, clinic). | Yes (where they went)
eDisposition_16 | Destination facility (name/ID). | Maybe (stratify by hospital)
eDisposition_21, eDisposition_22 | Additional response mode descriptors (e.g., lights/sirens used to or from scene). | Maybe (severity proxy)
eDisposition_32 | Emergency department disposition (e.g., admitted, discharged). | Yes (high‑level outcome)
eDisposition_27, eDisposition_28, eDisposition_29, eDisposition_30 | Unit disposition and reason, patient refusal, etc. | Maybe (filter 911 vs IFT)
eOutcome_01 | Hospital outcome (e.g., alive, dead). | Yes (clinical outcome)
eOutcome_02 | Hospital disposition (e.g., ICU, floor, OR). | Yes (severity / LOS proxy)
eOutcome_11 | Date/Time of Hospital Admission – true inpatient admit timestamp. | Yes (cohort filter; only valid rows kept)
eOutcome_16 | Date/Time of Hospital Discharge. | Maybe (LOS for small subset)
eOutcome_18 | Date/Time of Emergency Department Admission. | Yes (ED timing vs dispatch/turnaround)
ePatient_15 | Patient’s home county of residence. | Maybe (stratification by geography)
ePatient_16 | Patient’s home zip/postal code. | Maybe (urban vs rural)
ePayment_01 | Primary method of payment (Medicare, private, self‑pay, etc.). | Maybe (equity questions)
ePayment_50 | Total charges or payment category (implementation‑specific). | Maybe (if charges included)
eResponse_05 | Type of service requested (911 response, interfacility, intercept, etc.). | Yes (restrict to 911 emergencies)
eResponse_07 | Unit transport and equipment capability (ALS/BLS, ground/air). | Maybe (ALS vs BLS performance)
eResponse_23 | Response mode to scene (e.g., lights/sirens). | Maybe (severity proxy)
eScene_01 | Incident location type (home, street, nursing home, etc.). | Maybe (context)
eScene_06, eScene_07, eScene_08, eScene_09 | Scene census tract, GPS, etc.; detailed scene location descriptors. ​ | No (unless spatial analysis)
eSituation_02 | Possible injury (injury vs medical). | Yes (separate trauma vs medical)
eSituation_07 | Chief complaint anatomic location. | Maybe
eSituation_08 | Chief complaint organ system. | Maybe
eSituation_13 | Provider’s primary impression (working diagnosis). | Yes (case‑mix adjustment)
eSituation_20 | Cardiac arrest flag in situation section (context for arrest cases). ​ | No (handled via eArrest elements)
eSituation_01 | Date/Time of symptom onset / last known well. | Maybe (onset‑to‑care delay)
eSituation_18 | Incident/patient acuity (critical, emergent, non‑emergent). | Yes (acuity vs delays)
eDisposition_17 | Number of patients transported from scene by this EMS unit. | Maybe (exclude multi‑patient incidents if you want simplicity)